## Slide 1
07/09/2022
MyHealthNB
Go to Green Plan

## Slide 2: Agenda
Product & Design
Production Stability
Quality Review
Outstanding Items
2

## Slide 3: Quality Review

## Slide 4: Quality Review
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
Code Review | Hamdan Nathersa | In progress | Automated code review complete Reviewing results toward next steps |  | 30-Aug
Testing Quality | Poorna Muthukumar | In progress | 67% Complete |  | 21-Oct
Communication Quality | Srikanth | Complete |  |  | 15-July

## Slide 5: Product Updates

## Slide 6: Product Design
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
MSD-2453 - Logic Design LOA 0 (Un-verified accounts) Exists in Client Registry | Roland | On hold | This will be part of the Next gen CIAM stack. |  | Q1 ‘23
MSD-2807 – Login MFA Enablement | Srikanth/Hamdan | In progress | QA Regression testing in progress Enabled Login MFA in the existing build (V1.4) in QA |  | 16-Sep
MSD-2819 Decouple Terms of Use Prompt | Roland | In progress | Deploying the changes to QA |  | 05-Sep
MSD-2454/IOSD-1144 - Emails not being sent/security codes not validating | Srikanth/Hamdan | In progress | QA Regression testing in progress The fix will be part of the V2.0 build of IO |  | 16-Sep

## Slide 7: Product Design
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
MSD-2819 Enable Login History, Trusted Device | Srikanth | In Progress | WIP in QA |  | 05-Sep
MSD-2456/IOSD-1264 - Logic Design LOA 0 (Error 10114) | Roland | On hold | This will be part of the Next gen CIAM stack. |  | Q1 ‘23
MSD-2591/IOSD-1267: Logic Design - Re-registration Issue With Registration Code Field | Roland | On hold | This will be part of the Next gen CIAM stack. |  | Q1 ‘23
MSD-2819 - Geo Location Enablement | Hamdan | On hold | This will be part of the Next gen CIAM stack. |  | Q1 ‘23

## Slide 8: Production Stability

## Slide 9: Production Stability
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
MSD-2691: V1.4 Rollback after-effects (mismatch of users in IDaaS systems) | James | On hold | Waiting for MyHealthNB for the next steps |  | 31-Aug

## Slide 10: Outstanding Items from last release

## Slide 11: Defects & Enhancements
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
V1.4.1 Defects | Srikanth K | In progress | Reviewed the open items |  | 31-Aug
MSD-2713: French characters not allowed in password\Allowable characters | Paolo | Simeo QA Progress | QA Regression testing in progress |  | 31-Aug
MSD-1663 - Scheduled Processes_MyHealthNB Account About To Be Deleted Email | Appu/Paolo | Simeo QA Progress | QA Regression testing in progress |  | 31-Aug
MSD-1664 - Scheduled processes_MyHealthNB Account About To Be Inactivated Email | Appu/Paolo | Simeo QA Progress | QA Regression testing in progress |  | 31-Aug

## Slide 12: Defects & Enhancements
Work Steam | Action Owner | Status | Actions Planned/Taken | RAG | End Date
MSD-1632 Orphan Record Deletion | Srikanth | On Hold | MH decided not to use this solution until further notice. Hence paused the cronjobs. |  | 
MSD-1799 - Error Codes | Chelsea | Deferred | This will be part of the Next gen CIAM stack. |  | Q1 ‘23
Helpdesk Enablement | Roland/Hamdan | On Hold | This will be part of the Next gen CIAM stack. |  | Q1 ‘23
MSD-2036: Clicking back button takes users to the account profile | Nagendra/Paolo | In Progress | QA Regression testing in progress |  | 31-Aug

## Slide 13: Appendix

## Slide 14: Status # of active tickets
Status | #
Cancelled | 5
CR | 1
Deferred | 6
Deployed to Prod | 2
Done, Pending Simeio QA | 25
Duplicate | 2
In Progress | 6
On Hold | 1
Recommend to Defer | 15
Waiting for MH | 3
Grand Total | 66
This is the # of V1.4 open issues and enhancements, and tickets related to production stability (problem tickets, defects in prod)

## Slide 15: Thank You